|  |  |  |
| --- | --- | --- |
| **Milestone Schedule Descriptions** | | |
| **Line #** | **Line Description** | **AODA Description** |
| 1 | Engage Architects | Bar 1 within the Gantt chart shows the task of prime architect selection in the spring of 2023 |
| 2 | Phase 1- Design Guidelines | Bar 2 within the Gantt chart shows Phase 1- Design Guidelines started in the fall of 2023 |
| 3 | Phase 2- Building Design | Bar 3 within the Gantt chart depicts task of Phase 2- Building Design started in fall of 2023 and concluding in spring 2024 |
| 4 | Detailed Design | Bar 4 within the Gantt chart depicts the task of detailed design & contract documents completing in the summer of 2025. |
| 5 | Ministry Approval to Proceed to Tender | Bar 5 within the Gantt chart depicts the task of ministry approval to proceed to tender completing in summer of 2025. |
| 6 | Building Permit | Bar 6 within the Gantt chart depicts the task of building permit issuance completing in the spring of 2027 |
| 7 | Tender | Bar 7 within the Gantt chart depicts the task of tendering to general contractors starting & completing in the fall of 2027 |
| 8 | Construction | Bar 8 within the Gantt chart depicts the task of construction starting in winter of 2028 and culminating in the summer of 2029 |
| 9 | School Opening | Bar 9 within the Gantt chart depicts the school opening in Fall 2029 |