| Image Gallery Descriptions |  |  |
| --- | --- | --- |
| Doc # | Title | AODA Description |
| 01 | 3D Massing | Exterior 3D massing depicting both the gymnasium addition looking from the northwest of playfield. |
| 02 | Site Plan | Site plan drawing looking down from above depicting the school & playfield after the project is completed. |
| 03 | First Floor Plan | Architectural first floor plan looking down from above depicting instructional & operations spaces situated on the first floor after the project is completed. |
| 04 | Second Floor Plan | Architectural second floor plan looking down from above depicting instructional & operations spaces situated on the second floor after the project is completed. |
| 05 | Library Interior Rendering | Interior rendering showing a double-height space of the library |
| 06 | Gymnasium Interior Rendering | Interior rendering showing the new gymnasium with views to playing fields |
| 07 | Exterior Rendering Gymnasium | Exterior rendering from northwest of gymnasium addition looking from the playfield. |

| Milestone Schedule Descriptions |  |  |
| --- | --- | --- |
| Line # | Line Description | AODA Description |
| 1 | Engage Architects | Bar 1 within the Gantt chart shows prime architect selection occurring in Q2 2023 |
| 2 | New School Review Team | Bar 2 within the Gantt chart shows New School Review Team commencing at Starting Q3 2023 and completing at end of Q3 2024. |
| 3 | Schematic Design Approval | Bar 3 within the Gantt chart depicts task of schematic design approval completing at end of Q3 2023. |
| 4 | Detailed Design & Contract Documents | Bar 4 within Gant chart shows task of detailed design starting in Q42023 and completing in Q2 2025 |
| 5 | Ministry Approval to Proceed | Bar 5 within Gant chart shows task of ministry approval starting in Q2 2025 and to completing in Q3 2025 |
| 6 | Building Permit | Bar 6 within the Gantt chart shows Building Permit starting in Q1 2025 completing in Q3 2025. |
| 7 | Construction Tender | Bar 7 within the Gantt chart shows the task of construction tender starting Q3 2025 and completing in mid Q4 2025 |
| 8 | Construction | Bar 8 within the Gantt chart shows new school construction starting in mid Q4 2025 and completing in Q3 2027 |
| 9 | Project Completion | Bar 9 within the Gantt chart shows project completion in Q3 2027 |