| Milestone Schedule Descriptions |  |  |
| --- | --- | --- |
| Line # | Line Description | AODA Description |
| 1 | Engage Architects | Bar 1 within the Gantt chart refers to the consultant selection process. Prime architect was appointed in the spring of 2022. |
| 2 | Community Consultation | Bar 2 within the Gantt chart refers to the dialogue process with stakeholders. Community consultation was conducted in the summer of 2022. |
| 3 | Schematic Design Approval | Bar 3 within the Gantt chart refers to the schematic design approval milestone which is necessary to allow the detailed design to start. |
| 4 | Site Plan & Building Permit | Bar 4 within the Gantt chart is the site plan control and building permit process, duration is from September 2023 to September 2025. |
| 5 | Detailed Design | Bar 5 within the Gantt chart is the duration to complete the detailed design. Starting from September 2022 and completing by the end of 2025. |
| 6 | Ministry Approval to Proceed | Bar 6 within the Gantt chart refers to the ministry approval to proceed to tender completing in fall of 2025. |
| 7 | Construction Tender | Bar 7 within the Gantt chart depicts the task of tendering to general contractors starting in January of 2026 and completing in May of 2026. |
| 8 | Construction | Bar 8 within the Gantt chart depicts the task of construction starting in May of 2026 and completing in the summer of 2028. |
| 9 | School Opening | Bar 9 within the Gantt chart depicts the new addition being occupied by the school in September of 2028. |