**Projected Timeline as of July 3, 2020\***

May – Established Multi-Disciplinary School Reopening Committee

June 17 – Shared survey with parents/guardians and staff

June 18 – Shared survey with Grade 7-12 students and adult high school students

June 19 – Ministry of Education released approach to reopening schools for the 2020-21 school year

June 30 – All surveys close and Research begins to review and analyze results

July – School Reopening Committee to use Ministry guidelines and community feedback to develop a comprehensive reopening plan

July 3 – Subcommittees to have draft plans in to the Reopening Committee

July 13 – Union and Federation partners invited to participate in Reopening Committee meeting to share feedback

July 13 – meeting with Toronto Public Health for input on preliminary plans

July 15 – First draft of reopening plans shared with Trustees at Special Committee of the Whole

Week of July 27 – Meeting with Ministry of Education to review preliminary plans

Week of July 27 – Pre-registration survey for parents about intentions for September opening

August 4 – Final draft of reopening plans shared with Trustees at Special Committee of the Whole; TDSB provides reopening plan to Ministry of Education for approval

August – Provide opportunities for communities to learn about reopening plans

August 14 – Communicate students’ school schedules

September 8\*\* -- TDSB schools open

Ongoing – Adjust according to public health guidelines

\*Subject to change

\*\*EDU has not approved any school year calendars at this time