|  |  |  |
| --- | --- | --- |
| **Line #** | **Line Description** | **AODA Description** |
| 1 | Engage Architects | Bar 1 within the Gantt chart depicts Insurance Remediation and Reconstruction from Pre-Summer 2020 to Spring 2024. Prime architect was selected in the Spring of 2020. |
| 2 | Community Consultation | Bar 2 shows Community consultation was conducted in the Winter and Spring of 2022. |
| 3 | Schematic Design Approval | Bar 3 depicts that Schematic Design Approval was achieved in the early Spring of 2022. |
| 4 | Detailed Design | Bar 4 within the Gantt chart depicts the task of detailed design starting in Winter 2021 and continuing until the Winter of 2023. |
| 5 | Ministry Approval to Proceed to Tender | Bar 5 within the Gantt chart depicts the task of ministry approval to proceed to tender beginning in Summer 2023 and ending in Fall 2023. |
| 6 | Building Permit | Bar 6 within the Gantt chart depicts the task of building permit issuance starting in the Spring of 2023 continuing into the Winter of 2023. |
| 7 | Tender Close | Bar 7 within the Gantt chart depicts the task of tendering to general contractors closing in Spring 2024. |
| 8 | Construction | Bar 8 within the Gantt chart depicts the task of construction starting in the Spring of 2024 and ending early 2027 (prior to Spring). |
| 9 | School Opening | Bar 9 within the Gantt chart depicts the school being occupied for early 2027. |