|  |  |  |
| --- | --- | --- |
| **Line #** | **Line Description** | **AODA Description** |
| 1 | Engage Architects | Bar 1 within the Gantt chart is blank. Prime architect was selected in the spring of 2017. |
| 2 | Community Consultation | Bar 2 within the Gantt chart is blank. Community consultation was conducted in the spring of 2021. |
| 3 | Schematic Design Approval | Bar 3 within the Gantt chart depicts task of schematic design approval from the Board completing in summer of 2021. |
| 4 | Detailed Design & Contract Documents | Bar 4 within the Gantt chart depicts the task of detailed design & contract documents continuing into the fall of 2022. |
| 5 | Ministry Approval to Proceed to Tender | Bar 5 within the Gantt chart depicts the task of ministry approval to proceed to tender beginning and ending in spring of 2023. |
| 6 | SPA Approval & Building Permit | Bar 6 within the Gantt chart depicts the task of site plan approval and building permit issuance continuing into the spring of 2023. |
| 7 | Tender Close | Bar 7 within the Gantt chart depicts the task of tendering to general contractors starting in spring of 2023 and culminating late spring/early summer of 2023. |
| 8 | Relocation to Vaughn Road Academy | Bar 8 within the Gantt chart depicts the task of relocating Hodgson Middle School to Vaughn Road Academy starting and culminating in the summer of 2023. |
| 9 | Construction | Bar 9 within the Gantt chart depicts the task of construction starting in summer of 2023 and culminating summer of 2025. |
| 10 | Relocation Back to Hodgson MS | Bar 10 within the Gantt chart depicts the task of relocating Hodgson Middle School from Vaughn Road Academy back to Hodgson Middle School starting and culminating in the summer of 2025. |