|  |  |  |
| --- | --- | --- |
| **Milestone Schedule Descriptions** | | |
| **Line #** | **Line Description** | **AODA Description** |
| 1 | Engage Architects | Bar 1 within the Gantt chart is blank. Prime architect was selected in the fall of 2018. |
| 2 | Community Consultation | Bar 2 within the Gantt chart is blank. Community consultation was conducted in the summer of 2019. |
| 3 | Schematic Design Approval | Bar 3 within the Gantt chart depicts task of schematic design approval from the Board completed in summer of 2019. |
| 4 | Detailed Design & Contract Documents | Bar 4 within the Gantt chart depicts the task of detailed design & contract documents completing in the winter of 2022. |
| 5 | Ministry Approval to Proceed to Tender | Bar 5 within the Gantt chart depicts the task of ministry approval to proceed to tender completing in summer of 2022. |
| 6 | SPA Approval & Building Permit | Bar 6 within the Gantt chart depicts the task of site plan approval and building permit issuance completing in the fall of 2022. |
| 7 | Tender Close | Bar 7 within the Gantt chart depicts the task of tendering to general contractors starting & completing in the winter of 2022/2023. |
| 8 | Construction | Bar 8 within the Gantt chart depicts the task of construction starting in spring of 2023 and culminating in the winter of 2024/2025. |
| 9 | School Opening | Bar 9 within the Gantt chart depicts the new addition being occupied by the school in the winter of 2024/2025. |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |