|  |  |  |
| --- | --- | --- |
| **Image Gallery Descriptions** | | |
| **Doc #** | **Title** | **AODA Description** |
| 001 | Site Plan & Context | Architectural site plan looking down from above depicting the school & adjacent spaces |
| 002 | Heritage Summary | A summary of key elements to be restored as part of this reconstruction. |
| 003 | Stacked Plan |  |
| 004 | Basement Floor Plan | Architectural basement plan looking down from above depicting instructional & operations spaces situated on the first floor after the project is completed. |
| 005 | 1st Floor Plan | Architectural first floor plan looking down from above depicting instructional & operations spaces situated on the first floor after the project is completed. |
| 006 | 2nd Floor Plan | Architectural second floor plan looking down from above depicting instructional & operations spaces situated on the second floor after the project is completed. |
| 007 | 3rd Floor Plan | Architectural third floor plan looking down from above depicting instructional & operations spaces situated on the first floor after the project is completed. |
| 008 | 4th Floor Plan | Architectural fourth floor plan looking down from above depicting instructional & operations spaces situated on the first floor after the project is completed. |
| 009 | Perspective – Reconstructed Auditorium | Architectural interior perspective view showing the new auditorium in use |
| 010 | Reconstruction Activity | Current construction activity |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| **Milestone Schedule Descriptions** | | |
| **Line #** | **Line Description** | **AODA Description** |
| 1 | Engage Architects | Bar 1 within the Gantt chart refers to the consultant selection process. Prime architect was appointed in the spring of 2020. |
| 2 | Community Consultation | Bar 2 within the Gantt chart refers to the consultation and dialogue process with stakeholders. Community consultation was conducted in the winter/spring of 2022. A status presentation was made in March 2023 |
| 3 | Schematic Design Approval | Bar 3 within the Gantt chart refers to the schematic design approval – necessary to allow the design development to start. This took place in winter/spring 2022 |
| 4 | Detailed Design & Contract Documents | Bar 4 within the Gantt chart depicts the task of detailed design & contract documents - completing in the fall of 2023. Note that aspects of the project have been in the detailed design stage since 2020 and this activity will tie into the main project |
| 5 | Ministry Approval to Proceed to Tender | Bar 5 within the Gantt chart depicts the task of ministry approval to proceed to tender completing in fall of 2023 |
| 6 | Building Permit | Bar 6 within the Gantt chart depicts the task of site plan approval and building permit issuance completing in the spring of 2024. |
| 7 | Tender Close | Bar 7 within the Gantt chart depicts the task of tendering to general contractors starting & completing in the winter of 2023/2024. |
| 8 | Construction | Bar 8 within the Gantt chart depicts the task of construction starting in early 2024 and culminating in the summer of 2026. Note that aspects of the project have been under construction since 2020 and this activity will tie into the main project |
| 9 | School Opening | Bar 9 within the Gantt chart depicts the new addition being occupied by the school in the fall of 2026. |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |